## Overview
Sheet | Description | Purpose
1. Sample work plan | This is a sample workplan that includes the NMDR project steps. Note that that this is an iterative process, involving: collaboration across different stakeholders; continued improvement and maintenance to streamline and standardize data collection, collation, storage and analysis based on current best practice; testing the system to ensure it is fit for purpose; and training and supporting end users to ensure the system is used. | Develop an NMDR workplan that all stakeholders are aligned around.
2. Sample alternative work plan | Alternate work plan focused on activities | Develop an NMDR workplan that all stakeholders are aligned around.
3. Sample budget sheet | It is unlikely that the NMCP and MoH will have in-house capacity to manage the development and continued M&E of the system roll-out. This sample budget sheet shows how each activity has an associated cost. To bear in mind that this is a flexible example and should be adapted to the country context, with specific tasks such as data integration and end user training duplicated for each of the different modules integrated into the NMDR. In addition, items might need to be purchased (such as hardware or computer software) to ensure the smooth running of the system and use by end users. | To determine the cost of the initial development of the NMDR, and the ongoing maintenance, data integration, and training requirements for a sustainable NMDR.
4. Example workshop activities for data integration | Some countries have had success holding workshops of 1–2 weeks to integrate different modules into the NMDR. This sheet shows the activities that countries can carry out during the workshop. | Plan a workshop for data integration.
5. NMDR data itemization and planning | This is a template to: 1. List out the individual data sets that the selected indicators are calculated from 2. Document the current reporting flow of the data (including frequency and granularity) 3. Document the proposed MDR flow (including frequency and granularity) 4. Document the number of new electronic forms to develop, and the number of system integrations required | To move from the step of selecting and mapping indicators (sheet 2) to the steps of: 1. Finalizing the MDR scope 2. Determining how the data will ultimately flow into the MDR 3. Identifying the number of MDR new electronic reporting forms / system integrations to develop can begin to be estimated (which impacts timelines, developer effort needed, budget)
6. Example Data Dictionary | This is an example of a detailed data dictionary to be developed in the NMDR. If we are digitizing new forms, we will want to include a detailed data dictionary of the variable, value types, form organization etc. to guide the developer. It is not recommened to just provide them with paper form examples as this leaves a lot of room for interpretation and leads to more feedback cycles. For forms where we are simply pulling in data from another system, we can usually extract the data dictionary from the source system (or even export/import the entire dictionary if the systems are compatible). | Detail out each digital form design to guide the developer in building it.
Note on A1: This would be an ideal situation. Could be used by countries in their funding bids, but it's unlikely that countries will be able to do this. -Lilli Holst So this should be distinguished from the rest (or even removed). -Lilli Holst

## 1. Sample work plan
| Roles |  | Q(Year 1) |  |  |  | Q (Year 2) |  |  |  | Q (Year 3) onwards |  |  |  | Costs | Sources of finance
Phases and activities | Parties responsible | Collaborators | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Phase 1: Planning the NMDR
1. Identify and convene stakeholders | bar: Q(Year 1) 1
2. Create a shared vision for the NMDR and its intended users | bar: Q(Year 1) 1
3. Establish governance mechanism | bar: Q(Year 1) 1
4. Establish steering committee, a working groups, national champion | bar: Q(Year 1) 1
5. High level data audit and prioritization | bar: Q(Year 1) 1
6. Create a partner activity map | bar: Q(Year 1) 1
7. Define NMDR scope | bar: Q(Year 1) 1
8. Develop a costed work plan | bar: Q(Year 1) 1
Phases 2: Initial NMDR set up and data integration
1. Select and set up the platform for the NMDR | bar: Q(Year 1) 2 to Q(Year 1) 4
2. Confirm selection of initial thematic area(s) (module) and convene sub-group | bar: Q(Year 1) 2 to Q(Year 1) 4
3. In-depth module-specific data audit and mapping | bar: Q(Year 1) 2 to Q(Year 1) 4
4. Elaborate key users and data use cases within module | bar: Q(Year 1) 2 to Q(Year 1) 4
5. Configure/develop the module into the NMDR | bar: Q(Year 1) 2 to Q(Year 1) 4
5.1 Module setup (defining data dictionary and indicators) | bar: Q(Year 1) 2 to Q(Year 1) 4
5.2 Consolidate, clean and map historical data | bar: Q(Year 1) 2 to Q(Year 1) 4
5.3 Historical data importation | bar: Q(Year 1) 2 to Q(Year 1) 4
5.4 Define future state data flow (periodic imports, continuous integration with a source system, direct data entry); design and implement future data flow processes | bar: Q(Year 1) 2 to Q(Year 1) 4
5.5 Develop, refine, and extend dashboards to specific needs; iterate | bar: Q(Year 1) 2 to Q(Year 1) 4
6. Test | bar: Q(Year 1) 2 to Q(Year 1) 4
7. Roll-out and training | bar: Q(Year 1) 2 to Q(Year 1) 4
Phase 3: Intermediate NMDR development: integrating additional modules
1. Decide which additional thematic areas and indicators to include | bar: Q (Year 2) 1 to Q (Year 2) 4
2. In-depth module-specific data audit and mapping | bar: Q (Year 2) 1 to Q (Year 2) 4
3. Elaborate key users and data use cases within module | bar: Q (Year 2) 1 to Q (Year 2) 4
4. Configure/develop the modules into the NMDR in a phased approach. For each module, this includes: | bar: Q (Year 2) 1 to Q (Year 2) 4
- Module set-up (defining data dictionary and indicators)
- Consolidate, clean and map data
- Data integration
- Future state data flow implementation
- Develop, refine and extend dashboards to specific needs; iterate
5. Test and iterate on modules with stakeholders and end users | bar: Q (Year 2) 2 to Q (Year 2) 4
6. Roll-out and training | bar: Q (Year 2) 2 to Q (Year 2) 4
Phase 4: Advanced NMDR development: governance and sustainability
1. Continue to develop and maintain the NMDR | bar: Q (Year 2) 2 to Q (Year 3) onwards 4
2. Training and deployment. This involves: | bar: Q (Year 2) 2 to Q (Year 3) onwards 4
- Developing adequate product documentation
- Training of trainers workshop(s) at the central level
- Training workshops at a sub-national level
- Developing frameworks or guidelines for the review and supervision of data recording practices to ensure ongoing data quality and data-use
- Regular data review meetings to identify issues or areas for improvement
- SOPs for maintenance and channels to promote continuous feedback to improve and refine the system
- Strategies for continuous monitoring and evaluation of the system to understand how the NMDR is being used, and to measure its impact and its overall usefulness for malaria surveillance

## 2. Alternative work plan
Phase | Activities | Description | Workshop details | Estimated timeline | Deliverable | Number of days
Phase 1: Prerequisites | Initial analysis | Mapping of the different data sources, including the content (thematic area and indicators), the format, the frequency of updating, the mode of transmission, and the structures responsible for the collection and management of each dataset | Two-day workshop to present the project to stakeholders, to make an initial inventory of relevant and available data sources, and to initiate the needs analysis of the national program | [month 1] | Data Dictionary | 4
|  | National program needs analysis, with recommendations on 1) the technical solution chosen for the data warehouse, 2) the architecture and content of the warehouse in terms of modules to be retained, 3) the hosting solution | Logistics cost for approx. 20 people | [month 2] | National Program Needs Analysis Report | 4
Phase 1: Prerequisites | Common project roadmap | Update of the detailed roadmap, containing the main activities and the timetable |  | [month 2] |  | 2
Phase 1: Prerequisites | Technical stack | Description of the technical stack used in the project (repository, data integration tools, visualization tools, hosting, etc.) |  | [months 2 - 3] | Detailed architecture of the data warehouse, including the hosting solution | 2
Phase 1: Prerequisites | Governance | Steering committee bringing together the different units and actors (steering committee and/or technical working group), with documentation of the organization, roles and responsibilities | Steering committee meeting to validate the committee's terms of reference, the roadmap and timetable, and the proposed warehouse architecture | [months 3 - 4] |  | 2
Phase 2: Setup | Technical framework of the NMDR: Setting up the body | Evaluation of the existing server infrastructure |  |  |  | 1
|  | Implementation workshop (3 days): * Data source mapping and module 1 | Logistics cost for approx. 10 people | [months 4 - 5] | Mapping data sources | 4
|  |  | Presence/facilitation by 2 technical experts and local consultant |  | Module 1 configured | 4
|  | Configuration of the new DHIS2 instance (or other technical solution chosen to host the NMDR) |  |  |  | 2
Phase 2: Setup | Technical workshop 1: 3 module configuration | Preparatory work for workshop |  |  |  | 2
|  | Technical workshop (3 days) configuration: * Metadata configurations, * Loading data, * Dashboard design | Logistics cost for approx. 15 people | [months 5 - 6] |  | 1
|  |  | Facilitation by technical expert and local consultant |  | Modules 3-5 configured | 5
|  |  | Online support from 1 expert |  |  | 1
| Consolidation work | Finalization and quality assurance of modules Working sessions and skills transfer (adoption, analysis, maintenance, etc.) | Working session (1 day) with approx. 5 technicians |  |  | 2
|  |  | Technical work after workshop |  |  | 6
Phase 2: Setup | Technical workshop 2: 3 module configuration | Preparatory work for workshop |  |  |  | 2
|  | Technical workshop (3 days) configuration: * Metadata configurations, * Loading data, * Dashboard design | Logistics cost for approx. 15 people | [months 7 - 8] |  | 1
|  |  | Presence/facilitation by technical expert and local consultant |  | Modules 6-8 configured | 5
|  |  | Online support from 1 expert |  |  | 3
| Consolidation work | Finalization and quality assurance of modules Working sessions and skills transfer (adoption, analysis, maintenance, etc.) - technical work after workshop | Working session (1 day) with approx. 5 technicians |  |  | 2
|  |  | Technical work after workshop |  |  | 6
Phase 2: Setup | Technical workshop 3: 3 module configuration | Preparatory work for workshop |  |  |  | 2
|  | Technical workshop (3 days) configuration: * Metadata configurations, * Loading data, *Dashboard | Logistics cost for approx. 15 people | [months 9 - 10] |  | 1
|  |  | Facilitation by technical expert and local consultant |  | Modules 9-12 configured | 5
|  |  | Online support from 1 expert |  |  | 3
| Consolidation work | Finalization and quality assurance of modules Working sessions and skills transfer (adoption, analysis, maintenance, etc.) - technical work after workshop | Working session (1 day) with approx. 5 technicians |  |  | 2
|  |  | Technical work after workshop |  |  | 6
Phase 2: Setup | Technical workshop 4: 3 module configuration | Preparatory work for workshop |  |  |  | 2
|  | Technical workshop (3 days) configuration: * Metadata configurations, * Loading data, * Dashboard design | Logistics cost for approx. 15 people | [months 11 - 12] |  | 1
|  |  | Facilitation by technical expert and local consultant |  | Modules 13-15 configured | 5
|  |  | Online support from 1 expert |  |  | 3
| Consolidation work | Finalization and quality assurance of modules Working sessions and skills transfer (adoption, analysis, maintenance, etc.) - technical work after workshop | Working session (1 day) with approx. 5 technicians |  |  | 2
|  |  | Technical work after workshop |  |  | 6
Phase 2: Setup | Technical workshop 5: 3 module configuration | Preparatory work for workshop |  |  |  | 2
|  | Technical workshop (3 days) configuration: * Metadata configurations, * Loading data, * Dashboard design | Logistics cost for approx. 15 people | [months 13 - 14] |  | 1
|  |  | Facilitation by technical expert and local consultant |  | Modules 16-17 configured | 5
|  |  | Online support from 1 expert |  |  | 3
| Consolidation work | Finalization and quality assurance of modules Working sessions and skills transfer (adoption, analysis, maintenance, etc.) - technical work after workshop | Working session (1 day) with approx. 5 technicians |  |  | 2
|  |  | Technical work after workshop |  |  | 6
Phase 2: Setup | Finalization of the NMDR | Preparatory work for workshop |  |  | Comprehensive training program for national program staff and other services and partners | 2
|  | Technical workshop (3 days) on data quality * Final review of data quality for all modules * Data validation * Incorporation of the needs expressed during the finalization workshop. | Logistics cost for approx. 15 people | [months 15 - 16] |  | 1
|  |  | Facilitation by technical expert and local consultant |  |  | 4
|  |  | Technical work after workshop |  |  | 2
Phase 2: Setup | Validation of the NMDR | National validation workshop (4-5 days) + training * Brings together technicians and non-technicians (data users) so that they can see for each module whether their needs are taken into account and correctly displayed in the dashboards. * Training for skills transfer to the national program: on the final dashboards, reading and interpretation of data | Logistics cost for 20 people | [months 17 - 18] | Comprehensive Data Warehouse Technical Documentation | 2
|  |  | Presence/facilitation by 2 technicians and local consultant |  |  | 5
|  | Incorporation of the needs expressed during the validation workshop | Technical work after workshop |  |  | 4

## 3. Sample budget sheet
| Costs (external staff responsible for setting up and managing the NMDR) |  | Additional experts required
Role | IT expert responsible for the DHIS2 system | M&E expert familiar with the DHIS2 system | Person 3 e.g. LMIS expert | Person 4 e.g Server admin | Person 5
Phases and activities | Days | Days | Days | Days | Days
Phase 1: Planning the NMDR
1. Identify and convene stakeholders
2. Create a shared vision for the NMDR and its intended users
3. Establish governance mechanism
4. Establish steering committee, a working groups, national champion
5. High level data audit and prioritization
6. Create a partner activity map
7. Define NMDR scope
8. Develop a costed work plan
Phases 2: Initial NMDR set up and data integration
1. Select and set up the platform for the NMDR
2. Confirm selection of initial thematic area(s) (module) and convene sub-group
3. In-depth module-specific data audit and mapping
4. Elaborate key users and data use cases within module
5. Configure/develop the module into the NMDR
5.1 Module setup (defining data dictionary and indicators)
5.2 Consolidate, clean and map historical data
5.3 Historical data importation
5.4 Define future state data flow (periodic imports, continuous integration with a source system, direct data entry); design and implement future data flow processes
5.5 Develop, refine, and extend dashboards to specific needs; iterate
6. Test
7. Roll-out and training
Phase 3: Intermediate NMDR development: integrating additional modules
1. Decide which additional thematic areas and indicators to include
2. In-depth module-specific data audit and mapping
3. Elaborate key users and data use cases within module
4. Configure/develop the modules into the NMDR in a phased approach. For each module, this includes:
- Module set-up (defining data dictionary and indicators)
- Consolidate, clean and map data
- Data integration
- Future state data flow implementation
- Develop, refine and extend dashboards to specific needs; iterate
5. Test and iterate on modules with stakeholders and end users
6. Roll-out and training
Phase 4: Advanced NMDR development: governance and sustainability
1. Continue to develop and maintain the NMDR
2. Training and deployment. This involves:
- Developing adequate product documentation
- Training of trainers workshop(s) at the central level
- Training workshops at a sub-national level
- Developing frameworks or guidelines for the review and supervision of data recording practices to ensure ongoing data quality and data-use
- Regular data review meetings to identify issues or areas for improvement
- SOPs for maintenance and channels to promote continuous feedback to improve and refine the system
- Strategies for continuous monitoring and evaluation of the system to understand how the NMDR is being used, and to measure its impact and its overall usefulness for malaria surveillance
Total (person days and costs)
Additional costs (such as hardware or software required by the team)
Description | Number of units | Total cost
Laptops (if needed for analysis)
Tablets (if needed for additional data collection)
Smart Phones (if needed for additional data collection)
ArcGIS or other GIS software (e.g. QGIS)
Server / hosting costs
Meeting costs (planning, stakeholder convening, validation, etc.)
Technical workshop costs
Total cost

## 4. Example worshop activites fo
Activities | Day
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Provide an overview of the process of setting up an NMDR.
Explain the current malaria data repository in the country and the configuration of the DHIS2 instance that has been created.
Review the existing data and data gaps.
Identify additional data that the team would like to transfer to the national malaria data repository.
Add the data from the HMIS to the DHIS2 NMDR by matching indicators and data elements, creating data elements and input forms.
Test the data flow between the HMIS and the DHIS2 NMDR.
Achieve interoperability between the HMIS and the DHIS2 NMDR.
Test the interoperability between the HMIS and the DHIS2 NMDR.
Develop dashboards, for example, on morbidity, mortality, and intervention coverage.
Continue developing the dashboards.
Decide on data validation rules.
Review the work carried out during the workshop.
Decide on the next steps to take.

## 5. NMDR data itemization and pl
Module | Form/data set name | Description | Institution source | Data collection frequency | Is historical data available? | Source granularity | Proposed NMDR granularity | Current electronic reporting/ storage method | Analytical tools required | NMDR data flow | NMDR technical consultant effort | Prioritization
Case surveillance (HMIS) | Malaria monthly report | Aggregated malaria case data compiled from facility register and community health worker forms |  | Monthly | Yes | Facility | Same as source | HMIS (DHIS2) |  | HMIS DHIS2 → NMDR DHIS2 | System integration (with HMIS) | 1
| Health centre admission form | Inpatient cases at health facility level |  | Monthly | Yes | Facility | Same as source, malaria data only | HMIS (DHIS2) |  | HMIS DHIS2 → NMDR DHIS2 |  | 1
| Hospital admission form | Inpatient cases at hospital level |  | Monthly | Yes | Facility | Same as source, malaria data only | HMIS (DHIS2) |  | HMIS DHIS2 → NMDR DHIS2 |  | 1
| Antenatal care | Pregnant cases from ANC visits |  | Monthly | Yes | Facility | Same as source, malaria data only | HMIS (DHIS2) |  | HMIS DHIS2 → NMDR DHIS2 |  | 1
| Weekly surveillance form | Suspected cases, confirmed cases, and deaths for <5 and >5 |  | Weekly | Yes | Facility | Same as source, malaria data only | HMIS (DHIS2) |  | HMIS DHIS2 → NMDR DHIS2 |  | 1
Entomological | Larval collection | Larval collection, classification and density |  | Ad-hoc | Yes | Sentinel site | Same as source | Excel |  | Direct entry into NMDR DHIS2 (via web capture, Excel import, or DHIS2 Capture mobile app) | Digitize new form | 2
| Adult collection | Adult collection, classification and density |  | Ad-hoc | Yes | Sentinel site | Same as source | Excel |  | Direct entry into NMDR DHIS2 (via web capture, Excel import, or DHIS2 Capture mobile app) | Digitize new form | 2
| Insecticide resistance | Insecticide resistance by insecticide |  | Ad-hoc | Yes | Sentinel site | Same as source | Excel |  | Direct entry into NMDR DHIS2 (via web capture, Excel import, or DHIS2 Capture mobile app) | Digitize new form | 2
| Insecticide resistance – intensity concentration | Insecticide resistance by insecticide and concentration |  | Ad-hoc | Yes | Sentinel site | Same as source | Excel |  | Direct entry into NMDR DHIS2 (via web capture, Excel import, or DHIS2 Capture mobile app) | Digitize new form | 2
| Insecticide resistance – molecular and biochemical mechanism | Molecular mechanism of resistance |  | Ad-hoc | Yes | Sentinel site | Same as source | Excel |  | Direct entry into NMDR DHIS2 (via web capture, Excel import, or DHIS2 Capture mobile app) | Digitize new form | 2
| Insecticide resistance – synergist-insecticide bioassay | Insecticide resistance synergy between compounds |  | Ad-hoc | Yes | Sentinel site | Same as source | Excel |  | Direct entry into NMDR DHIS2 (via web capture, Excel import, or DHIS2 Capture mobile app) | Digitize new form | 2
Commodities | Health facility pharmacy stock card | Daily stock movements |  | Daily | Yes | Facility | Monthly, facility | SIGLUS (OpenLMIS) |  | Commodities data warehouse -> MDR DHIS2 | System integration (with LMIS data warehouse) | 3
| Monthly requisition report | Monthly stock requisition |  | Monthly | Yes | Facility | Monthly, district | SIMAM Access |  | Commodities data warehouse -> MDR DHIS2 |  | 3
| RDT Consumption (MIT ficha) | RDT Consumption |  | Monthly | Yes | Facility | Monthly, district | SIMAM Access |  | Commodities data warehouse -> MDR DHIS2 |  | 3
| AL (ACT) Consumption | ACT consumption |  | Monthly | Yes | Facility | Monthly, district | SIMAM Access |  |  |  | 3
Population | Census Data | Population |  | Every 10 years | Yes | District | Same as source | SIS-MA DHIS2 |  | HMIS DHIS2 -> MDR DHIS2 | System integration (with HMIS) | 4
IRS | IRS data | Spray targets, spray coverage, population coverage (NMCP + GBM + PMI) |  | Annual | Yes | District | Same as source | Excel |  | Direct entry into MDR DHIS2 (via web capture, Excel import, of DHIS2 Capture mobile app | Digitize new form | 5
LLIN | LLIN UAC Distribution | LLIN distribution |  | Every 3 years | Yes | Neighborhood | District | Excel |  | Direct entry into MDR DHIS2 (via web capture, Excel import, of DHIS2 Capture mobile app | Digitize new form | 5
| LLIN durability studies | LLIN durability |  | Every 3 years? | Yes | District | Same as source | Excel |  | Direct entry into MDR DHIS2 (via web capture, Excel import, of DHIS2 Capture mobile app | Digitize new form | 5
Communications | Communication reports | Communication events held |  | Quarterly | No | Provincial | Same as source | N/A - reports |  | Direct entry into MDR DHIS2 (via web capture, Excel import, of DHIS2 Capture mobile app | Digitize new form | 6
DQA (New) | DQA - National | Data quality |  | Annual | No | National | Same as source | N/A |  | Direct entry into MDR DHIS2 (via web capture, Excel import, of DHIS2 Capture mobile app | Digitize new form | 7
| DQA - Provincial | Data quality |  | Biannual | No | Provincial | Same as source | N/A |  |  | Digitize new form | 7
| DQA – District | Data quality |  | Quarterly | No | District | Same as source | N/A |  |  | Digitize new form | 7
| DQA - Facility | Data quality |  | Monthly | No | Facility | Same as source | N/A |  |  | Digitize new form | 7
Supervision (New) | Integrated supervision | TBD |  | TBD | No | TBD | Same as source | N/A |  | Direct entry into MDR DHIS2 (via web capture, Excel import, of DHIS2 Capture mobile app | Digitize new form | 8
| M&E supervision | TBD |  | TBD | No | TBD | Same as source | N/A |  | Direct entry into MDR DHIS2 (via web capture, Excel import, of DHIS2 Capture mobile app | Digitize new form | 8
| Case management supervision | Supervision checklist for clinical care |  | TBD | No | TBD | Same as source | N/A |  | Direct entry into MDR DHIS2 (via web capture, Excel import, of DHIS2 Capture mobile app | Digitize new form | 8
| Entomological supervision | TBD |  | TBD | No | TBD | Same as source | N/A |  | Direct entry into MDR DHIS2 (via web capture, Excel import, of DHIS2 Capture mobile app | Digitize new form | 8
Surveys | Health Facility Survey | Quality of care |  | Every 2-3 years | Yes | Facility | TBD | Excel |  | Ad-hoc Import into MDR DHIS2 using Excel templates | Digitize new form | 9
| Malaria Indicator Survey | Malaria indicators |  | Every 2-3 years | Yes | Bairro | Province | Excel or csv (SAS export) |  | Ad-hoc Import into MDR DHIS2 using Excel templates | Digitize new form | 9
| Service Availability and Readiness Assessment | Service Availability and Readiness |  | Every 3 years | Yes | Bairro | Province | Excel or csv (SAS export)? |  | Ad-hoc Import into MDR DHIS2 using Excel templates | Digitize new form | 9
| COMSA | Mortality data |  |  | Yes | Facility | Province |  |  | Ad-hoc Import into MDR DHIS2 using Excel templates | Digitize new form | 9
Climate | Country_rainfalll-temperature.csv | Mean rainfall and temperature data per district | ERA5 / CHIRPS | Monthly |  |  |  | Raster files and district shapefiles | Spatial software (QGIS or similar) or R |  |  | 9

## 6. Example data dictionary
Form Section | Variable label | Variable definition | Variable Type | Dropdown options | Mandatory | Validation or logic rules
Enrollment | Collection Date | Date of adult vector collection | Date |  | Yes
| Sector/Section/Block | Sector or section where adult vectors were collected | Text
| Nearest sentinel site (if out in the community) | Name of the nearest sentinel site, if our in the community | Text
| Team Name/ Number | Team Name or Number (e.g. Team A or Team 2) | Text
| Team Leader Name | The first name and surname of the team leader in charge of the larval collection | Text
| Index Case ID (if Re-Active) | The NMC Case ID of the Index Case, if adult vector collection is being done as part of a Focus Investigation | Text
| Has the area received IRS? | Indicate if houses in a 5km radius received IRS during the most recent spray campaign | Radio buttons | Yes/No/Unknown
| If Sprayed, Date last sprayed | Enter the date the area received IRS | Date |  |  | Hide if 'Has area received IRS' != Yes
| Insecticide sprayed | Type of insecticide used, if any. If insecticide is not listed, select 'Other' and specify in the next field | Option set (dropdown) | DDT Pyrethroid Unknown Other (specify) |  | Hide if 'Has area received IRS' != Yes
| Other Insecticide | Enter the other type of insecticide used | Text |  |  | Hide is 'Insecticide sprayed' != Other
| Rain in area (mm) last 24 hours | Estimated number of mm of rain this area received in the last 24 hours | Numeric
| Wind conditions | Wind conditions during the time of adult vector collection | Option set (dropdown) | None; Moves leaves; Moves twigs; Moves small branches; Moves large branches
Event Registration | Collection Date | Date that the adult vector collection was conducted | Date |  |  | Default to today's date
| GPS Coordinates | GPS coordinates of area where adult collection was conducted | Coordinates |  |  | For Repeat Events 2 and 3, copy over GPS coordinates from Stage 1 since they only collect coordinates once for the area on the form
Sample Information | Sample ID | ID of the sample, as assigned by the field team | Text
| Collection Method | Indicate the collection method used to collect the samples | Option set (dropdown) | (IC) Indoor collection; (ISC) Indoor Spray Collections = ISC; (OS) Outside Shelter/Kraal; (PT) Pit trap; (CP) Clay Pot; (T) Tyre; (EWT) Exit Window Trap; (LC) Landing catches; (BNT) Baited Net Trap
| Nearest Breeding Site Distance (not the sentinel site) | Estimate the distance of the structure from the nearest breeding site that is NOT a sentinel site) | Option set (dropdown) | (1) 0 – 100m; (2) 100 – 500m; (3) 500m – 1km; (4) more than 1km
Structure characteristics (if applicable) | Structure/room type | Indiciate the primary use of the structure in which collection was done. If structure type is not listed above, select 'Other' and specify in the next field) | Option set (dropdown) | (LR) Living room; (SR) Sleeping Room; (ST) Storeroom; (K) Kitchen; (G) Attic; (S) Animal Shelter; (OV) Outdoor Vegetation; (OTH) Other |  | Text input if other (specify) is selected
| Other type | Indicate the other type of structure | Text |  |  | Only display if 'Type' == Other
| Surface type | Indicate the surface type of the structure where the collection was made. If structure type is not listed, select N/A | Option set (dropdown) | (C/Z) Cement/Zinc; (C/S) Cement/Straw; (B/Z) Banco/Zinc; (B/S) Banco/Straw; (TH) Thatched Hut; (RT) Roof tile (NA) Not Applicable
| Sprayed/Unsprayed | Indicate if the surface was sprayed or unsprayed | Option set (radio button) | Sprayed Unsprayed
| Number of people | Number of people living in the household | Integer
Total An. gambiae complex vectors collected | An. gambiae -MALES | Total number of Anopheles gambie males collected at the structure | Integer
| An. gambiae - FEMALES FED | Total number of Anopheles gambie FED females collected at the structure | Integer
| An. gambiae - FEMALES UNFED | Total number of Anopheles gambie unFED females collected at the structure | Integer
Total An. funestus group vectors collected | An. funestus - MALES | Total number of Anopheles funestus males collected at the structure | Integer
| An. funestus - FEMALES FED | Total number of Anopheles funestus FED females collected at the structure | Integer
| An. funestus - FEMALES UNFED | Total number of Anopheles funestus unFED females collected at the structure | Integer
Non-vector other Anopheles collected | Other Anopheles - MALES | Total number of non-vector Anopheles males collected at the structure | Integer
| Other Anopheles - FEMALES FED | Total number of non-vector Anopheles FED females collected at the structure | Integer
| Other Anopheles - FEMALES UNFED | Total number of non-vector Anopheles unFED females collected at the structure | Integer
Non-vector Culicines collected | Culicine - MALES | Total number of non-vector Culicine males collected at the structure | Integer
| Culicine - FEMALES FED | Total number of non-vector Culicine FED females collected at the structure | Integer
| Culicine - FEMALES UNFED | Total number of non-vector Culicine unFED females collected at the structure | Integer
Approval and Capture Details | Notes on the collection | Additional notes of interest regarding the collection | Text
| Supervisor Name | Individual supervising and reviewing LM01 data | Username
| Captured by | User who is capturing the information | Username |  | Yes
| Date of Capture | Date that the form is being entered into the system | Date |  | Yes